## Team Backlog (Air Conditioning)
# | Task Name | Assignee | Task Status | Expected time to finish | Actual time to finish
1 | DIO Driver | Anas | Done | 2023-04-18 | 2023-04-18
2 | Interrupts Driver | Omar | Done | 2023-04-18 | 2023-04-18
3 | Timer 0 Driver | Mustafa | Done | 2023-04-18 | 2023-04-18
4 | Timer 2 Driver | Mohab | Done | 2023-04-18 | 2023-04-18
5 | Buzzer Driver | Mohab | Done | 2023-04-19 | 2023-04-19
6 | LCD Driver | Mohab/Omar | Done | 2023-04-25 | 2023-04-25
7 | ADC Driver | Mustafa | Done | 2023-04-25 | 2023-04-25
8 | Keypad Driver | Anas | Done | 2023-04-25 | 2023-04-25
9 | Application | Mustafa/Omar | Done | 2023-04-25 | 2023-04-25
10 | Unit Tests | Mohab | Done | 2023-04-25 | 2023-04-25

## Data Validation Range (hidden)
Task Status
To Do
Doing
Done